## Project List_(0130)
☞ 24' ESS/UPS Project List
Product | Customer | Project Name | Con | Rack | BCP /BBP | RJP | Module | Cell | Ah | Start Date | End Date | ship ready date | Cell | Remark | (Sella2_Low Cell) | (Sella2_Old Cell) | KF_02 New Cell | Sella 2 New Cell | Slotting
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2023-11-06 | 2023-11-30 | 2024-01-05 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q1
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2023-12-05 | 2024-01-05 | 2024-01-12 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q1
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2023-12-18 | 2024-01-15 | 2024-01-22 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q2
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2024-01-03 | 2024-01-25 | 2024-01-29 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q2
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2024-01-17 | 2024-02-13 | 2024-02-20 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q2
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2024-01-29 | 2024-02-23 | 2024-03-02 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q2
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2024-02-21 | 2024-03-18 | 2024-03-25 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q3
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 30 | 3 |  | 360 | 15840 | 103Ah | 2024-03-07 | 2024-03-29 | 2024-04-06 | Sella 2 new cell |  |  |  |  | 15840 | 24' Q3
ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 |  | 35 | 2 |  | 420 | 18480 | 103Ah | 2024-03-19 | 2024-04-12 | 2024-04-19 | Sella 2 new cell |  |  |  |  | 18480 | 24' Q3
ESS_Rack | ABB Sp. Z.o.o. | DART 2.5MW |  | 13 | 4 |  | 156 | 6864 | 103Ah | 2024-02-14 | 2024-03-04 | 2024-03-05 | Sella 2 new cell |  |  |  |  | 6864 | 24' Q1
ESS_Rack | ABB Sp. Z.o.o. | DART 2.5MW |  | 7 |  |  | 84 | 3696 | 103Ah | 2024-02-14 | 2024-03-04 | 2024-03-05 | KF_02 New |  |  |  | 3696 |  | 24' Q2
ESS_Rack | Powertech | Conoco Philips Spinning Reserve BESS |  | 42 | 7 |  | 504 | 22176 | 103Ah | 2024-04-09 | 2024-05-03 | 2024-05-10 | Sella 2 new cell |  |  |  |  | 6864 | 24' Q3
UPS_Rack | ACE Power Engineering Pte Ltd | RED project |  | 9 |  |  | 36 | 1260 | 85Ah | 2023-12-18 | 2023-12-26 | 2024-03-15 | KF_02 New |  |  |  | 1260 |  | 24' Q1
UPS_Rack | ACE Power Engineering Pte Ltd | RED project |  | 6 | 2(BCP) 10(BBP) |  | 24 | 840 | 85Ah | 2024-02-01 | 2024-02-23 | 2024-03-15 | KF_02 New |  |  |  | 840 |  | 24' Q1
UPS_Rack | ACE Power Engineering Pte Ltd -> Vertiv (Hong Kong) Limited | RED project -> iAdvantage TKO 131 800kV |  | 6 | 2 | 2 | 24 | 840 | 85Ah | 2023-12-18 | 2023-12-26 | 2024-01-26 | KF_02 New | Ace Power -> Vertiv 배정 변경 |  |  | 840 |  | 24' Q1
UPS_Rack | Daitron Co., LTD | Shinagawa |  | 4 | 4 |  | 16 | 560 | 85Ah | 2024-02-01 | 2024-02-13 | 2024-02-15 | KF_02 New |  |  |  | 560 |  | 24' Q1
UPS_Rack | ABB Australia Pty Ltd | Sure Power 160S Racks |  | 16 | 2 |  | 80 | 2560 | 85Ah | 2024-04-01 | 2024-04-05 | 2024-04-19 | KF_02 New |  |  |  | 2560 |  | 24' Q2
UPS_Rack | ACE Power Engineering Pte Ltd | RED project |  | 6 | 10 |  | 24 | 840 | 85Ah | 2023-02-01 | 2024-02-16 | 2024-02-19 | KF_02 New |  |  |  | 840 |  | 24' Q1
100
136
53
214
| Apr | [6 empty] | Jun |  |  |  |  | Q2 MP Plan
| 16W | 17W | 19W | 20W |  |  | 21W | 23W | [8 empty] | 267
| 1.6 | 7.1 | 7.1 | 7.1 |  |  | 7.1 | 7.1 |  |  |  |  | 37.1
| 1.6 | 7.1 | 7.1 | 7.7 |  |  | 7.7 | 7.7 |  |  |  |  | 38.9
[13 empty] | 0 |  |  |  | 36
0
231
10164

## Pack&System Plan (Project)
[13 empty] | 24Y | [43 empty] | 공동연차 | [19 empty] | 공동연차 | [48 empty] | ER 예정 구간 | [23 empty] | 공동연차 | [87 empty] | 하계휴가(임시)
| Line | Type | Customer | Project Name | P/O | PN | Description | Remark | Sum | Status |  | Inv | 1W | [6 empty] | 2W | [6 empty] | 3W | [6 empty] | 4W | [6 empty] | 5W | [6 empty] | 6W | [6 empty] | 7W | [6 empty] | 8W | [6 empty] | 9W | [6 empty] | 10W | [6 empty] | 11W | [6 empty] | 12W | [6 empty] | 13W | [6 empty] | 14W | [6 empty] | 15W | [6 empty] | 16W | [6 empty] | 17W | [6 empty] | 18W | [6 empty] | 19W | [6 empty] | 20W | [6 empty] | 21W | [6 empty] | 22W | [6 empty] | 23W | [6 empty] | 24W | [6 empty] | 25W | [6 empty] | 26W | [6 empty] | 27W | [6 empty] | 28W | [6 empty] | 29W | [6 empty] | 30W | [6 empty] | 31W | [6 empty] | 32W | [6 empty] | 33W | [6 empty] | 34W | [6 empty] | 35W | [6 empty] | 36W | [6 empty] | 37W | [6 empty] | 38W | [6 empty] | 39W | [6 empty] | 40W | [6 empty] | 41W | [6 empty] | 42W | [6 empty] | 43W | [6 empty] | 44W | [6 empty] | 45W | [6 empty] | 46W | [6 empty] | 47W | [6 empty] | 48W | [6 empty] | 49W | [6 empty] | 50W | [6 empty] | 51W | [6 empty] | 52W
 | time axis 2023-12-31 to 2024-12-28
| MD | PACK |  |  |  | KMD255151E220L2 | KOL Module A Type 103Ah
| MD | PACK |  |  |  | KMD255151E220L3 | KOL Module B Type 103Ah
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30017 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | Finish | 1 | 360
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30018 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | Finish | 2 | 360
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30019 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | Finish | 3 | 282 | 2024-01-02: 42; 2024-01-03: 36
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30020 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | Finish | 4 |  | 2024-01-03: 6; 2024-01-04: 42; 2024-01-05: 42; 2024-01-08: 42; 2024-01-09: 42; 2024-01-10: 42; 2024-01-11: 42; 2024-01-12: 42; 2024-01-15: 42; 2024-01-16: 18
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30021 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | Finish | 5 |  | 2024-01-16: 24; 2024-01-17: 42; 2024-01-18: 42; 2024-01-19: 42; 2024-01-22: 42; 2024-01-23: 42; 2024-01-24: 42; 2024-01-25: 42; 2024-01-26: 42
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30022 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 | ing | 6 |  | 2024-01-29: 42; 2024-01-30: 42; 2024-01-31: 42; 2024-02-02: 24; 2024-02-05: 42; 2024-02-06: 42; 2024-02-07: 42; 2024-02-08: 42; 2024-02-14: 42
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30023 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 |  | 7 |  | 2024-02-23: 42; 2024-02-26: 42; 2024-02-27: 42; 2024-02-28: 42; 2024-02-29: 18; 2024-03-05: 42; 2024-03-06: 42; 2024-03-07: 42; 2024-03-08: 42; 2024-03-11: 6
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30024 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 360 |  | 8 |  | 2024-03-11: 36; 2024-03-12: 42; 2024-03-13: 42; 2024-03-14: 42; 2024-03-15: 42; 2024-03-18: 42; 2024-03-19: 42; 2024-03-20: 42; 2024-03-21: 30
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30025 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 420 |  | 9 |  | 2024-03-21: 12; 2024-03-22: 42; 2024-03-25: 42; 2024-03-26: 42; 2024-03-27: 42; 2024-03-28: 42; 2024-03-29: 42; 2024-04-03: 42; 2024-04-04: 42; 2024-04-05: 42; 2024-04-08: 30
| MD | ESS_MD | ABB Sp. Z.o.o. | DART 2.5MW | 23P30067 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 156 |  |  |  | 2024-02-15: 36; 2024-02-16: 42; 2024-02-19: 42; 2024-02-20: 36
| MD | ESS_MD | ABB Sp. Z.o.o. | DART 2.5MW | 23P30067 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 논산 | 84 |  |  |  | 2024-02-20: 6; 2024-02-21: 42; 2024-02-22: 36
| MD | ESS_MD | Powertech | Conoco Philips Spinning Reserve BESS | 24P30006 | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY WITH PUNCHING CRP CELL | 음성 NEW | 504 |  |  |  | 2024-04-09: 42; 2024-04-11: 42; 2024-04-12: 42; 2024-04-15: 42; 2024-04-16: 42; 2024-04-17: 42; 2024-04-18: 42; 2024-04-19: 42; 2024-04-22: 21; 2024-04-23: 21; 2024-04-24: 21; 2024-04-25: 21; 2024-04-26: 21; 2024-04-29: 21; 2024-04-30: 21; 2024-05-02: 21
| MD | ESS_MD | R&D | UL 9540 시료 | 24P30007 | KMD255166E222F3 | Product: KMD255166E222F3, 46TRAY WITH PUNCHING CRP CELL | 음성 old | 12 |  |  |  | 2024-02-29: 12
| MD | ESS_MD | R&D | UL 9540 시료 | 24P30007 | KMD255166E222F3-Dummy | Dummy module | Dummy | 12 |  |  |  | 2024-02-29: 12
| MD | ESS_MD | Pacific Energy Renewables WA Pty Ltd | Carnarvon Spare Parts | 24P30005 | KMD255125P220F0 | Product: KMD255125P220F0, 42TRAY MODULE | C/S Cell 배정 | 1 | bar: 2024-02-22
| MD | UPS_MD | Daitron Co., LTD | Shinagawa | 23P30083 | KMD255109P135A1 | Product : KMD255109P135A1, 40TRAY WITH PUNCHING CRP CELL |  | 16 | ing |  |  | 2024-02-01: 16
| MD | UPS_MD | ACE Power Engineering Pte Ltd | RED project | 23P30028 | KMD255109P135A1 | Product : KMD255109P135A1, 40TRAY WITH PUNCHING CRP CELL |  | 24 | ing |  |  | 2024-02-01: 24
| MD | UPS_MD | ABB Australia Pty Ltd | Sure Power 160S Racks | 23P30086 | KMD255100P132A1 | Product : KMD255100P132A1, 40TRAY WITH CRP PUNCHING CELL |  | 80 |  |  |  | 2024-04-01: 40; 2024-04-02: 40
| MD | UPS_MD | ABB s.r.o. | Kevlin X UPS Project | 23P30082 | KMD255109P135A1 | Product : KMD255109P135A1, 40TRAY WITH PUNCHING CRP CELL |  | 180 |  |  |  | 2024-02-02: 16; 2024-05-03: 24; 2024-05-07: 24; 2024-05-08: 24; 2024-05-09: 24; 2024-05-10: 24; 2024-05-13: 24; 2024-05-14: 20
0
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30017 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 | Finish | 1 | 30
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30018 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 | Finish | 2 | 30
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30019 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 | Finish | 3 | 12 | 2024-01-03: 3; 2024-01-05: 8; 2024-01-08: 7
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30020 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 | Finish | 4 |  | 2024-01-10: 8; 2024-01-12: 7; 2024-01-16: 8; 2024-01-18: 7
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30021 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 | ing | 5 |  | 2024-01-23: 8; 2024-01-25: 7; 2024-01-29: 8; 2024-01-31: 5; 2024-02-05: 2
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30022 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 |  | 6 |  | 2024-02-05: 5; 2024-02-07: 8; 2024-02-15: 8; 2024-02-19: 7; 2024-02-20: 2
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30023 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 |  | 7 |  | 2024-02-29: 8; 2024-03-06: 7; 2024-03-08: 7; 2024-03-12: 8
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30024 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 30 |  | 8 |  | 2024-03-14: 8; 2024-03-19: 7; 2024-03-21: 8; 2024-03-25: 7
분리형 | SYS | ESS_Rack | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30025 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 35 |  | 9 |  | 2024-03-27: 8; 2024-03-29: 10; 2024-04-02: 7; 2024-04-08: 7; 2024-04-11: 3
분리형 | SYS | ESS_Rack | ABB Sp. Z.o.o. | DART 2.5MW | 23P30067 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 13 |  |  |  | 2024-02-21: 8; 2024-02-23: 5
분리형 | SYS | ESS_Rack | ABB Sp. Z.o.o. | DART 2.5MW | 23P30067 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 논산 | 7 |  |  |  | 2024-02-27: 7
분리형 | SYS | ESS_Rack | Powertech | Conoco Philips Spinning Reserve BESS | 24P30006 | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | 음성 NEW | 42 |  |  |  | 2024-04-12: 7; 2024-04-16: 7; 2024-04-18: 6; 2024-04-22: 7; 2024-04-25: 5; 2024-04-29: 5; 2024-05-03: 5
| SYS | ESS_EP | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30017 | KBC11040003 | Product: KBC11040003(Std.ESS BCP 4000A, MA-DC-A067, Type-A) |  | 12 |  |  |  | 2024-01-25: 4; 2024-01-30: 3; 2024-03-07: 4; 2024-03-13: 1
| SYS | ESS_EP | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30017 | KBC11040004 | Product: KBC11040004(Std.ESS BCP 4000A, MA-DC-A067, Type-B) |  | 13 |  |  | 6 | 2024-02-16: 7
| SYS | ESS_EP | Pacific Energy Renewables WA Pty Ltd | LSO2 | 23P30017 | KBC11040005 | Product: KBC11040005(Std.ESS BCP 4000A, MA-DC-A067, Type-C) |  | 1 | bar: 2024-03-13
| SYS | ESS_EP | ABB Sp. Z.o.o. | DART 2.5MW | 23P30067 | KBC11040003 | Product: KBC11040003(Std.ESS BCP 4000A, MA-DC-A0 |  | 4 |  |  |  | 2024-02-28: 4
| SYS | ESS_EP | Powertech | Conoco Philips Spinning Reserve BESS | 24P30006 | KBC11040003 | Product: KBC11040003(Std.ESS BCP 4000A, MA-DC-A067, Type-A) |  | 7 |  |  |  | 2024-03-21: 4; 2024-03-28: 3
| SYS | UPS_Rack | Daitron Co., LTD | Shinagawa | 23P30083 | KST043515A14ADC02 | PRODUCT : KST043515A14ADC02 1P35S, 1C4R(140S) |  | 4 |  |  |  | 2024-02-06: 4
| SYS | UPS_Rack | ACE Power Engineering Pte Ltd | RED project | 23P30028 | KST043515A14ADC01 | Product : KST043515A14ADC01 1P35S, 1C4R(140S), IEC 62619, IEC62477-1, EMC Cetificate |  | 6 |  |  |  | 2024-02-06: 6
| SYS | UPS_Rack | ABB Australia Pty Ltd | Sure Power 160S Racks | 23P30086 | KST050588A15ADC01 | 85Ah 1P32S 1C5R Battery Rack |  | 16 |  |  |  | 2024-04-03: 8; 2024-04-05: 8
| SYS | UPS_Rack | ABB s.r.o. | Kevlin X UPS Project | 23P30082 | KST054644A15ADC01 | Product : KST054644A15ADC01 1P35S, 1C5R(175S), I |  | 0
| SYS | UPS_EP | Vertiv (Hong Kong) Limited | iAdvantage TKO 131 800kV | 23P30084 | KBC06018000 | Product : KBC06018000, T2-BCP1960 |  | 2 |  |  |  | 2024-01-03: 2
| SYS | UPS_EP | Vertiv (Hong Kong) Limited | iAdvantage TKO 131 800kV | 23P30084 | KRJ07503205 | Product : KRJ07503205, T2-RJP1960-4P |  | 2 |  |  |  | 2024-01-18: 2
| SYS | UPS_EP | Daitron Co., LTD | Shinagawa | 23P30083 | KBBZZZZZZ02 | Bank BMS Panel for UPS (w/ IO logik)_BLACK |  | 4 |  |  |  | 2024-02-06: 4
| SYS | UPS_EP | ACE Power Engineering Pte Ltd | RED project | 23P30051 | KBBZZZZZZ03 | Product : KBBZZZZZZ03 |  | 10 |  |  |  | 2024-02-20: 5; 2024-02-23: 5
| SYS | UPS_EP | ACE Power Engineering Pte Ltd | RED project | 23P30029 | KBC06018000 | Product : KBC06018000, T2-BCP1960 |  | 2 |  |  |  | 2024-02-23: 2
| SYS | UPS_EP | ABB Australia Pty Ltd | Sure Power 160S Racks | 23P30086 | KBC07540000 | 4000A Battery Connection Panel with extension box |  | 2 |  |  |  | 2024-04-03: 2
| SYS | UPS_EP | ABB s.r.o. | Kevlin X UPS Project | 23P30082 | KBC07540000 | 4000A Battery Connection Panel with extension box |  | 4 |  |  |  | 2024-04-12: 4
0
| SYS | ETC | R&D | UL 9540 시료 | 24P30007 | MS-BU-A039 | Product: KBP110050EB200 |  | 1 | bar: 2024-02-29
| SYS | ETC | R&D | UL 9540 시료 | 24P30007 | ASK-MA-HI-A004 | CASE ASSY,FUSE of Standard ESS 3C4R 103Ah Rack(2P22Sx12S) |  | 1 | bar: 2024-02-29
| SYS | ETC | Hitachi Energy Australia Pty Ltd |  | 24P30008 | ASK-MS-YB-A025 | BUSBAR ASSY, BCP, ADAPTER, 3C4R of Standard ESS |  | 2 |  |  |  | 2024-02-02: 2
Note on BU45: Win 11 적용
Note on BM54: 자재 입고 일정 미확정 필요 시 일정 변경

## UNIT CELL Plan
포장 작업
PO | Custormer | PartNumber | PartName | 공정 | 합계 | 시작 | 종료 | Status | Process | 진척도 |  | 1W | [5 empty] | 2W | [6 empty] | 3W | [6 empty] | 4W | [6 empty] | 5W | [6 empty] | 6W | [6 empty] | 7W | [6 empty] | 8W | [6 empty] | 9W | [6 empty] | 10W | [6 empty] | 11W | [6 empty] | 12W | [6 empty] | 13W | [6 empty] | 14W | [6 empty] | 15W | [6 empty] | 16W | [6 empty] | 17W | [6 empty] | 18W | [6 empty] | 19W | [6 empty] | 20W | [6 empty] | 21W | [6 empty] | 22W | [6 empty] | 23W | [6 empty] | 24W | [6 empty] | 25W | [6 empty] | 26W | [6 empty] | 27W | [6 empty] | 28W | [6 empty] | 29W | [6 empty] | 30W | [6 empty] | 31W | [6 empty] | 32W | [6 empty] | 33W | [6 empty] | 34W | [6 empty] | 35W | [6 empty] | 36W | [6 empty] | 37W | [6 empty] | 38W | [6 empty] | 39W | [6 empty] | 40W | [6 empty] | 41W | [6 empty] | 42W | [6 empty] | 43W | [6 empty] | 44W | [6 empty] | 45W | [6 empty] | 46W | [6 empty] | 47W | [6 empty] | 48W | [6 empty] | 49W | [6 empty] | 50W | [6 empty] | 51W | [6 empty] | 52W | [6 empty] | 1W | [6 empty] | 2W | [6 empty] | 3W | [6 empty] | 4W | [6 empty] | 5W | [6 empty] | 6W | [6 empty] | 7W | [6 empty] | 8W | [6 empty] | 9W | [6 empty] | 10W | [6 empty] | 11W | [6 empty] | 12W | [6 empty] | 13W | [6 empty] | 14W | [6 empty] | 15W | [6 empty] | 16W | [6 empty] | 17W | [6 empty] | 18W | [6 empty] | 19W | [6 empty] | 20W | [6 empty] | 21W | [6 empty] | 22W | [6 empty] | 23W | [6 empty] | 24W | [6 empty] | 25W | [6 empty] | 26W | [6 empty] | 27W | [6 empty] | 28W | [6 empty] | 29W | [6 empty] | 30W | [6 empty] | 31W | [6 empty] | 32W | [6 empty] | 33W | [6 empty] | 34W | [6 empty] | 35W | [6 empty] | 36W | [6 empty] | 37W | [6 empty] | 38W | [6 empty] | 39W | [6 empty] | 40W | [6 empty] | 41W | [6 empty] | 42W | [6 empty] | 43W | [6 empty] | 44W | [6 empty] | 45W | [6 empty] | 46W | [6 empty] | 47W | [6 empty] | 48W | [6 empty] | 49W | [6 empty] | 50W | [6 empty] | 51W | [6 empty] | 52W
[11 empty] | 수량 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28
24P30001 | BattTech | KCL216060EN1T01 | Tab punching cell, KCL216060EN1, Each tab, 4-Φ4 |  | 160 |  |  | PLAN |  | 100% | [380 empty] | 160
24P30001 | BattTech | KCL216060EN1T01 | Tab punching cell, KCL216060EN1, Each tab, 4-Φ4 |  | 160 |  |  | Actual |  | 100% | [380 empty] | 160
24P30002 | XBW srl | KCL255103EN1T01 | Tab punching cell, KCL255103EN1, Each tab, 4-Φ4 |  | 2352 |  |  | PLAN |  | 0% | [410 empty] | 1000 | 1000 |  |  | 352
24P30002 | XBW srl | KCL255103EN1T01 | Tab punching cell, KCL255103EN1, Each tab, 4-Φ4 |  | 0 |  |  | Actual |  | 0%

## Pack&System Plan (Model) (hidden)
Balance
사용
|  |  |  | KMD255137P222F0 | [5 empty] | PRJ | [45 empty] | 264
288
| Line | Type | 구분 | PartNumber (Agile) | PartName | ST | 합계 | 시작 | 종료 | Status | 진척도 | 비고 | 완료 | 27W | [6 empty] | 28W | [6 empty] | 29W | [6 empty] | 30W | [6 empty] | 31W | [6 empty] | 32W | [6 empty] | 33W | [6 empty] | 34W | [6 empty] | 35W | [6 empty] | 36W | [6 empty] | 37W | [6 empty] | 38W | [6 empty] | 39W | [6 empty] | 40W | [6 empty] | 41W | [6 empty] | 42W | [6 empty] | 43W | [6 empty] | 44W | [6 empty] | 45W | [6 empty] | 46W | [6 empty] | 47W | [6 empty] | 48W | [6 empty] | 49W | [6 empty] | 50W | [6 empty] | 51W | [6 empty] | 52W
 | time axis 2023-07-02 to 2023-12-30
KOL | MD | PACK | KOL | KMD255151E220L2 | 모듈,A타입,130255255G1,2P20S | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
KOL | MD | PACK | KOL | KMD255151E220L2 | 모듈,A타입,130255255G1,2P20S | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
KOL | MD | PACK | KOL | KMD255151E220L3 | KOL Module B Type 103Ah | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
KOL | MD | PACK | KOL | KMD255151E220L3 | KOL Module B Type 103Ah | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
우진 | MD | PACK | HP | FA-MD-A129 | MODULE,130255255G1,1P25S | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
우진 | MD | PACK | HP | FA-MD-A129 | MODULE,130255255G1,1P25S | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| MD | ESS | Std.ESS-CRP | KMD255151E220F1 | Product: KMD255151E220F1, 42TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255151E220F1 | Product: KMD255151E220F1, 42TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F1 | Product: KMD255166E222F1, 46TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | 1801 |  |  | Actual | #REF! |  |  | 2023-07-03: 68; 2023-07-04: 68; 2023-07-05: 68; 2023-07-06: 69; 2023-07-07: 58; 2023-07-10: 56; 2023-07-11: 68; 2023-07-12: 69; 2023-07-13: 68; 2023-07-14: 63; 2023-07-17: 68; 2023-07-18: 5; 2023-07-21: 44; 2023-07-24: 8; 2023-07-25: 68; 2023-07-26: 68; 2023-07-27: 56; 2023-07-28: 56; 2023-07-31: 56; 2023-08-01: 68; 2023-08-02: 42; 2023-08-03: 31; 2023-08-04: 31; 2023-08-14: 68; 2023-08-15: 32; 2023-08-24: 72; 2023-08-25: 72; 2023-08-31: 50; 2023-09-01: 68; 2023-09-04: 68; 2023-09-05: 68; 2023-09-06: 47 | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F1-TEMP | Product: KMD255166E222F1, 46TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F1-TEMP | Product: KMD255166E222F1, 46TRAY FRONT TERMINAL FORCED AIR COOLING MODULE WITH PUNCHING CRP CELL | #REF! | 12 |  |  | Actual | #REF! |  |  | 2023-07-10: 12 | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F2 | TBD | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F2 | TBD | #REF! | 564 |  |  | Actual | #REF! |  |  | 2023-08-15: 36; 2023-08-16: 68; 2023-08-17: 68; 2023-08-18: 68; 2023-08-21: 68; 2023-08-22: 68; 2023-08-23: 68; 2023-08-28: 68; 2023-08-29: 40; 2023-08-31: 12 | 0
| MD | ESS | Std.ESS-CRP | KMD255125P220F1 | Product: KMD255125P220F1, 42TRAY WITH PUNCHING CRP CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255125P220F1 | Product: KMD255125P220F1, 42TRAY WITH PUNCHING CRP CELL | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| MD | ESS | 포장 | 모듈 포장 |  | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS |  |  |  | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| MD | ESS | Std.ESS-CRP | KMD255137P222F0 |  | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255137P222F0 |  | #REF! | 4 |  |  | Actual | #REF! |  |  | 2023-07-21: 4 | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F0 | Product: KMD255166E222F0, 46TRAY MODULE | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | ESS | Std.ESS-CRP | KMD255166E222F0 | Product: KMD255166E222F0, 46TRAY MODULE | #REF! | 4 |  |  | Actual | #REF! |  |  | 2023-07-21: 4 | 0
| MD | UPS | 2020 UPS-CRP | KMD255100P132A1 | Product : KMD255100P132A1, 40TRAY FRONT TERMINAL PLATE CONDUCTOR MODULE WITH CRP PUNCHING CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | UPS | 2020 UPS-CRP | KMD255100P132A1 | Product : KMD255100P132A1, 40TRAY FRONT TERMINAL PLATE CONDUCTOR MODULE WITH CRP PUNCHING CELL | #REF! | 60 |  |  | Actual | #REF! |  |  | 2023-07-24: 60 | 0
| MD | UPS | 2020 UPS-CRP | KMD255103P133A1 | Product : KMD255103P133A1, 40TRAY FRONT TERMINAL MODULE WITH CRP PUNCHING CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | UPS | 2020 UPS-CRP | KMD255103P133A1 | Product : KMD255103P133A1, 40TRAY FRONT TERMINAL MODULE WITH CRP PUNCHING CELL | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| MD | UPS | 2020 UPS-CRP | KMD255109P135A1 | Product : KMD255109P135A1, 40TRAY FRONT TERMINAL PLATE CONDUCTOR MODULE WITH PUNCHING CRP CELL | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MD | UPS | 2020 UPS-CRP | KMD255109P135A1 | Product : KMD255109P135A1, 40TRAY FRONT TERMINAL PLATE CONDUCTOR MODULE WITH PUNCHING CRP CELL | #REF! | 340 |  |  | Actual | #REF! |  |  | 2023-07-18: 65; 2023-07-19: 73; 2023-07-20: 72; 2023-07-21: 30; 2023-08-29: 25; 2023-08-30: 75 | 0
3C4R | SYS | ESS | Std.ESS-RACK | KST200971F34AAB04 | 3C4R(Cover)CRP RACK, Product: KST200971F34AAB04 (Includes L | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
3C4R | SYS | ESS | Std.ESS-RACK | KST200971F34AAB04 | 3C4R(Cover)CRP RACK, Product: KST200971F34AAB04 (Includes L | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
2C6R(컨) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB04 | 2C6R (Cover) CRP Rack, Single type, Product Name: KST200971F26AAB05 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
2C6R(컨) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB04 | 2C6R (Cover) CRP Rack, Single type, Product Name: KST200971F26AAB05 | #REF! | 38 |  |  | Actual | #REF! |  |  | 2023-07-12: 10; 2023-07-13: 5; 2023-07-14: 5; 2023-07-19: 9; 2023-07-20: 9 | 0
2C6R(분리형) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | #REF! | #REF! |  |  | PLAN | #REF! |  | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
2C6R(분리형) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB12 | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | #REF! | 114 |  |  | Actual | #REF! |  |  | 2023-07-03: 8; 2023-07-04: 7; 2023-07-05: 6; 2023-07-10: 5; 2023-07-11: 5; 2023-07-17: 5; 2023-07-25: 5; 2023-07-26: 5; 2023-07-27: 5; 2023-07-28: 5; 2023-07-31: 5; 2023-08-01: 5; 2023-08-02: 5; 2023-08-03: 5; 2023-08-04: 5; 2023-08-17: 4; 2023-08-18: 4; 2023-08-25: 1; 2023-08-29: 6; 2023-08-30: 6; 2023-09-04: 4; 2023-09-05: 4; 2023-09-06: 4 | 0
2C6R(분리형) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB12-TEMP | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | #REF! | #REF! |  |  | PLAN | #REF! | 논산 | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
2C6R(분리형) | SYS | ESS | Std.ESS-RACK | KST200971F26AAB12-TEMP | CRP 103Ah 2P22S Separable 2C6R COVER / Link Type Rack | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
2C5R | SYS | ESS | Std.ESS-RACK | KST125736F25AAA06 | CRP Rack, Product Number: KST125736F25AAA06 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
2C5R | SYS | ESS | Std.ESS-RACK | KST125736F25AAA06 | CRP Rack, Product Number: KST125736F25AAA06 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
2C6R GEN1.1 | SYS | ESS | Std.ESS-RACK | KST200971F26AAB14 | 2C6R (Cover) CRP Gen1.1 Rack, Product Name: KST200971F26AAB14 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
2C6R GEN1.1 | SYS | ESS | Std.ESS-RACK | KST200971F26AAB14 | 2C6R (Cover) CRP Gen1.1 Rack, Product Name: KST200971F26AAB14 | #REF! | 25 |  |  | Actual | #REF! |  |  | 2023-08-23: 11; 2023-08-24: 11; 2023-08-31: 2; 2023-09-06: 1 | 0
| SYS | ESS | Std.ESS-BCP | KBC11040003 | Product: KBC11040003(Std.ESS BCP 4000A, MA-DC-A067, Type-A) | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-BCP | KBC11040003 | Product: KBC11040003(Std.ESS BCP 4000A, MA-DC-A067, Type-A) | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | ESS | Std.ESS-BCP | KBC11040004 | Product: KBC11040004(Std.ESS BCP 4000A, MA-DC-A067, Type-B) | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-BCP | KBC11040004 | Product: KBC11040004(Std.ESS BCP 4000A, MA-DC-A067, Type-B) | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | ESS | Std.ESS-BCP | KBC11040005 | Product: KBC11040005(Std.ESS BCP 4000A, MA-DC-A067, Type-C) | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-BCP | KBC11040005 | Product: KBC11040005(Std.ESS BCP 4000A, MA-DC-A067, Type-C) | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | ESS | Std.ESS-CONTAINER | KBN300971PF34AAB1 | Bank Containing 3C4R Rack, CRP 103Ah (2P22S 12M, | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-CONTAINER | KBN300971PF34AAB1 | Bank Containing 3C4R Rack, CRP 103Ah (2P22S 12M, | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | ESS | Std.ESS-CONTAINER | KCN529712MF26AAB1 | Containerized System (PJT : Billion Weichang) Model : KCN52 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-CONTAINER | KCN529712MF26AAB1 | Containerized System (PJT : Billion Weichang) Model : KCN52 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
sella 2 | SYS | ESS | Std.ESS-CONTAINER | KCN209711JF26AAB0 | Containerized System, Product Number : KCN209711JF26AAB0 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
sella 2 | SYS | ESS | Std.ESS-CONTAINER | KCN209711JF26AAB0 | Containerized System, Product Number : KCN209711JF26AAB0 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
22R Type | SYS | ESS | Std.ESS-CONTAINER | KCN489712LF26AAB0 | Containerized System, Product Number : KCN489712LF26AAB0 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-CONTAINER | KCN489712LF26AAB0 | Containerized System, Product Number : KCN489712LF26AAB0 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
20R Type | SYS | ESS | Std.ESS-CONTAINER | KCN409712JF26AAB0 | Containerized System, Product Number : KCN489712LF26AAB0 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | Std.ESS-CONTAINER | KCN409712JF26AAB0 | Containerized System, Product Number : KCN489712LF26AAB0 | #REF! | 1 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-17
18R | SYS | ESS | Std.ESS-CONTAINER | KCN369712JF26AAB0 | Containerized System, Product Number | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
18R | SYS | ESS | Std.ESS-CONTAINER | KCN369712JF26AAB0 | Containerized System, Product Number | #REF! | 1 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-20
24r gen1.1 | SYS | ESS | Std.ESS-CONTAINER | KCN489712LF26AAB1 | Containerized System, Product Number | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
24r gen1.1 | SYS | ESS | Std.ESS-CONTAINER | KCN489712LF26AAB1 | Containerized System, Product Number | #REF! | 2 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-20; 2023-08-31
22r gen1.1 | SYS | ESS | Std.ESS-CONTAINER | KCN449712KF26AAB1 | Containerized System, Product Number | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
22r gen1.1 | SYS | ESS | Std.ESS-CONTAINER | KCN449712KF26AAB1 | Containerized System, Product Number | #REF! | 2 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-20; 2023-08-25
| SYS | ESS | BPU | MS-BU-A039 | KBP110050EB200 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | ESS | BPU | MS-BU-A039 | KBP110050EB200 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | UPS | 2020 UPS | KST043515A14ADC01 | Product : KST043515A14ADC01 1P35S, 1C4R(140S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KST043515A14ADC01 | Product : KST043515A14ADC01 1P35S, 1C4R(140S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | 1 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-13
| SYS | UPS | 2020 UPS | KST050588A15ADC01 | Product : KST050588A15ADC01 1P32S, 1C5R(160S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KST050588A15ADC01 | Product : KST050588A15ADC01 1P32S, 1C5R(160S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | 12 |  |  | Actual | #REF! |  |  | 2023-07-27: 6; 2023-07-28: 6 | 0
| SYS | UPS | 2020 UPS | KST054644A15ADC01 | Product : KST054644A15ADC01 1P35S, 1C5R(175S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KST054644A15ADC01 | Product : KST054644A15ADC01 1P35S, 1C5R(175S), IEC 62619, IEC62477-1, EMC Cetificate | #REF! | 68 |  |  | Actual | #REF! |  |  | 2023-07-20: 7; 2023-07-21: 7; 2023-07-24: 7; 2023-07-25: 7; 2023-07-26: 7; 2023-07-27: 1; 2023-08-25: 2; 2023-08-28: 6; 2023-08-29: 6; 2023-08-30: 6; 2023-08-31: 5; 2023-09-01: 7 | 0
| SYS | UPS | 2020 UPS | KBBZZZZZZ01 | Bank BMS Panel for UPS (w/ IO logik)_RAL7035 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KBBZZZZZZ01 | Bank BMS Panel for UPS (w/ IO logik)_RAL7035 | #REF! | 1 |  |  | Actual | #REF! | [184 empty] | 0 | bar: 2023-07-06
| SYS | UPS | 2020 UPS | KBC07540000 | Product : KBC07540000, T2-BCP1960 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KBC07540000 | Product : KBC07540000, T2-BCP1960 | #REF! | 10 |  |  | Actual | #REF! |  |  | 2023-07-17: 1; 2023-07-18: 1; 2023-07-19: 1; 2023-07-20: 1; 2023-07-21: 1; 2023-07-26: 3; 2023-09-04: 1; 2023-09-05: 1 | 0
| SYS | UPS | 2020 UPS | KBC06018001 | Product : KBC06018001, T2-BCP2300 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | UPS | 2020 UPS | KBC06018001 | Product : KBC06018001, T2-BCP2300 | #REF! | 4 |  |  | Actual | #REF! |  |  | 2023-08-22: 1; 2023-08-23: 2; 2023-08-24: 1 | 0
| SYS | PACK | HP | FA-RH-A079 | 랙,130255255G1,1P25S | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | PACK | HP | FA-RH-A079 | 랙,130255255G1,1P25S | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | PACK | KOL | KFB15005001 | Fuse box, KOL, 1500VDC, 500A, 100kA, IP56 | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | PACK | KOL | KFB15005001 | Fuse box, KOL, 1500VDC, 500A, 100kA, IP56 | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0
| SYS | PACK | KOL | KBP100050EC204 | BPU, KOL, DNV, 1000VDC, Rated 500A | #REF! | #REF! |  |  | PLAN | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| SYS | PACK | KOL | KBP100050EC204 | BPU, KOL, DNV, 1000VDC, Rated 500A | #REF! | 0 |  |  | Actual | #REF! | [184 empty] | 0

## Capa
■ Capa 개선 전/후
분류 | 항목 | 구분 | Capa |  |  |  | Cell / Module 소요량
|  |  | As-is | Target | To-be | 개선율 | As-is | Target | To-be
Daily | Module | 2Line 8hr (2shift 1조) | 32 | 38 | 42 | 31.25% | 1408 | 1672 | 1848
|  | 2Line 10hr | 40 | 47 | 52 | 30% | 1760 | 2068 | 2288
|  | 주간 2Line 8hr 야간 1Line 10hr | 52 | 61 | 68 | 30.77% | 2288 | 2684 | 2992
|  | 주간 1Line 10hr 주간 1Line 8hr 야간 1Line 10hr |  |  | 74
|  | 주간 2Line 10hr 야간 2Line 10hr | 80 | 94 | 104 | 30% | 3520 | 4136 | 4576
| Rack | 8hr | 3 | 6 | 6 | 100% | 36 | 72 | 72
|  | 10hr | 3.75 | 7.5 | 7.5 | 100% | 45 | 90 | 90
Monthly (Working day 20일) | Module | 2Line 8hr | 640 | 760 | 840 | 31.25% | 28160 | 33440 | 36960
|  | 2Line 10hr | 800 | 950 | 1050 | 31.25% | 35200 | 41800 | 46200
|  | 주간 2Line 8hr 야간 1Line 10hr | 1040 | 1235 | 1365 | 31.25% | 45760 | 54340 | 60060
|  | 주간 2Line 10hr 야간 2Line 10hr | 1600 | 1900 | 2100 | 31.25% | 70400 | 83600 | 92400
| Rack | 8hr | 60 | 120 | 120 | 100% | 720 | 1440 | 1440
|  | 10hr | 75 | 150 | 150 | 100% | 900 | 1800 | 1800

## Sheet2
Application | Customer | Project Name | PN | BCP/BBP 수량 | 완료 | 예정 | Win_ver
ESS | Pacific Energy Renewables WA Pty Ltd | LSO2 | KBC11040003,4,5 | 26 | 13 | 13 | 10 | A | 12
ESS | ABB Sp. Z.o.o. | DART 2.5MW | KBC11040003 | 4 |  | 4 | 11 | B | 13
UPS | ACE Power Engineering Pte Ltd | RED project | KBC06018000 | 4 | 2 | 2 | 10 | C | 1
UPS | ACE Power Engineering Pte Ltd | RED project | KBBZZZZZZ03 | 10 |  | 10 | 10
UPS | Daitron Co., LTD | Shinagawa | KBBZZZZZZ02 | 4 |  | 4 | 10